## Bug Log
No | Scope / Function | Bug Description | Priority | Points | Date Found | Found By | (Resolved / Unresolved) | Resolved Date | Resolved By | Action Taken
Iteration 1
NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
Iteration 2
1 | SQL scripts (create tables, insert values/load-in file) | Unable to populate SQL database due to typo in one attribute | Low | 1 | 2013-09-17 | Zachery | Resolved | 2013-09-17 | Zachery | Correct the typo
2 | SQL scripts (create tables, insert values/load-in file) | Forgot to reset limit for smart BatchQuery | Low | 1 | 2013-09-25 | Nicholas | Resolved | 2013-09-25 | Zachery | Correct the error
3 | AddBidServlet.java | To Be: Redirect to view-my-bid.jsp | HIGH | 5 | 2013-09-27 | Zach | Resolved | 2013-09-27 | Kevin | Change the redirect
4 | EditBidServlet.java | To Be: Redirect to view-my-bid.jsp with value changed in the table | HIGH | 5 | 2013-09-27 | Zach | Resolved | 2013-09-27 | Kevin | Change the redirect
5 | BootstrapServlet.java | Validator for bid : hasNotEnoughEDollars during bootstrap when the respective csv value is empty, resulted in null pointer | CRITICAL | 10 | 2013-10-05 | Kevin | Resolved | 2013-10-05 | Zachery | Change validator
6 | BootstrapServlet.java | Inserting random.zip as upload input, never shown appropriate json output | Low | 1 | 2013-10-05 | Kevin | Resolved | 2013-10-05 | Zachery | Remove testcase in this sector, since the data will always be in correct format
Iteration 3
1 | AddBidServlet.java | if user input value below 10$, user get stuck in a blank page instead of my-page.jsp | Low | 1 | 2013-10-10 | Kevin | Resolved | 2013-10-12 | Kevin | Change the redirect
Iteration 4
1 | DropServlet | Cannot Drop | LOW | 1 | 2013-10-30 | Zach | Resolved | 2013-11-02 | Zachery | Debug dropSection.java
2 | Round 1 clearing Logic | The number of vacancies does not change. | LOW | 1 | 2013-10-31 | Kevin | Resolved | 2013-11-02 | Zachery | Debug script call to DB
3 | Error Message | Error Message is not shown for the missing or wrong values for edit bid | LOW | 1 | 2013-10-31 | Kevin | Resolved | 2013-11-01 | Yuning | Retrieve error message from DAO
Iteration 5
1 | Round 2 logic | Vacancy doesn't return the correct value after drop | LOW | 1 | 2013-11-05 | class UAT | Resolved | 2013-11-10 | Zachery | debug clearing logic
2 | Round 2 logic | Clearing price doesn't compute | LOW | 1 | 2013-11-05 | class UAT | Resolved | 2013-11-10 | Zachery | debug clearing logic
3 | BootstrapServlet.java | Bootstrap failed to filter invalid time | LOW | 1 | 2013-11-05 | class UAT | Resolved | 2013-11-10 | Nyein Su Aye | debug bootstrap servlet
4 | Bid status | App failed to let the user know the status of their bid (fail/success) | LOW | 1 | 2013-11-05 | class UAT | Resolved | 2013-11-10 | Kevin | Add in new tab for bid status in timetable
Iteration 6
1 | JSON web services | Minor bug in validation of JSON request and output | HIGH | 5 | 2013-11-12 | automated checker | Resolved | 2013-11-16 | Zachery | debug validation
2 | Search course | Search course filter by school not working | LOW | 1 | 2013-11-14 | Kevin | Resolved | 2013-11-16 | Zachery | debug searchCourseServlet

## Bug Summary Report
Iteration | Low | High | Critical | Total Score | Action Taken
1 | NA | NA | NA | NA | NA
2 | 3 | 2 | 1 | 23 | We stopped all development and fixed the bug immediately.
3 | 1 |  |  | 1 | NA
4 | 3 |  |  | 3 | NA
5 | 4 | 0 |  | 4 | NA
6 | 1 | 1 |  | 6 | NA

## Reference - Bugs Metrics
Severity | Description
Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues
High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
Critical Impact (10 points) | The system is down or is usable after a short period of time. We have to fix the bugs to continue.
Points Calculation: | Total = 1 x num (low) + 5 x num (high) + 10 x num (critical)
Points in iteration | Action
Points =< 5 | Fix during buffer time only.
5 < Points < 10 | Use the planned debugging time.
Points >= 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.