## Schedule Metrics
Iteration | Planned Days | Actual Days | Schedule Score (%) | Action Taken
#1 | 13 | 13 | 100% | Currently on track. Keep up with the progress.
#2 | 13 | 13 | 100% | Currently on track. Keep up with the progress.
#3 | 7 | 7 | 100% | Currently on track. Keep up with the progress.
#4 | 19 | 20 | 95% | Currently on track. Keep up with the progress.
#5 | 7 | 7 | 100% | Currently on track. Keep up with the progress.
#6 | 7 | 7 | 100% | Currently on track. Keep up with the progress.

## Schedule Metrics References
Schedule Metrics
Score(%) | Action
SM < 50 | 1.Immediately, inform your supervisor about the slip within 24 hours.
2.Then use the same mitigation as the category 50 < SM < 90 and seriously consider dropping tasks.
50 < SM <= 90 | 1.Re-estimate the tasks for the future iterations.
2.Deduct the number of days behind schedule from buffer days.
3.If there is no more buffer day, decide the functionalities to drop.
90 < SM <= 110 | Our estimates are fairly accurate, and we are roughly on track.
1.Add/Deduct the number of days behind schedule from buffer days.
2.If there is no more buffer day, decide the functionalities to drop
110 < SM <= 150 | Gross over-estimated the effort required.
1.Re-estimate the tasks for the future iterations.
2.Add the number of days gained to buffer days.
150 < SM | 1.Immediately, inform your supervisor about the slip within 24 hours.
2.Then use the same mitigation as the category 110 < SM < 150