## Slide 1
Final Presentation
Kevin Onggo (PM)
Kong Yu Ning
Nicholas Lee
Nyein Su Aye
Zachery Pang
G1T3

## Slide 2
Scope of Presentation
Schedule
Metrics
Use of Subversion
Others

## Slide 3: Schedule
1
2
3
4
5
Actual Vs Planned
Functionalities & Frameworks
Task Distribution
Task Allocation
Programming Hours
6
Problems Faced

## Slide 4
Chart: 
| Iteration 1 | Iteration 2 | Iteration 3 | Iteration 4 | Iteration 5 | Iteration 6
Planned | 13 | 13 | 7 | 19 | 11 | 7
Actual | 13 | 13 | 7 | 20 | 11 | 7
Actual vs Planned
A: 13
P: 13
A: 13
P: 13
A: 7
P: 7
A: 19
P: 20
A: 11
P: 11
A: 7
P: 7
1
Week 3-4
Week 5-6
Week 8-10
Week 11-12
Week 13
Notes: Explain the deviation, and more importantly why our schedule doesn’t have a regular chunk like 2 weeks.

## Slide 5
Iteration 1
1) Schedule Planning
2) Design & Diagram
3) Test Plan
Iteration 2
1) Bootstrap
2) Data Managers
3) Supervisor Meeting*
Iteration 3
1) CRUD Functions
2) JSON Response
3) Basic UI
4) Supervisor Meeting*
Iteration 4
1) Round 1 Logic
2) UI Enhancements
3) Heuristics*
4) Round 2 Logic
Iteration 5
1) Internal UAT
2) Supervisor Meeting*
3) Improvements
4) UAT*
5) Post UAT Debug
Iteration 6
1) Post Automated JSON Debug
2) Final Presentation Slides
14 Weeks
* Denotes major milestones
Actual vs Planned
1
Week 3-4
Week 5-6
Week 8-10
Week 11-12
Week 13
Week 7
Notes: Explain the deviation, and more importantly why our schedule doesn’t have a regular chunk like 2 weeks.

## Slide 6
Functionalities / Frameworks / External Libraries | 
Additional Functionalities | 
Framework | 
External Library | 1. ZIP4J
 | 2. Jquery
 | 3. Twitter Bootstrap
 | 4. OpenCSV
 | 5.GSON
 | 6. Apache FileUpload
 | 7. Apache ScriptRunner
 | 8. JDBC
2
Functionalities & Frameworks
Notes: Explain the deviation, and more importantly why our schedule doesn’t have a regular chunk like 2 weeks.

## Slide 7
Chart: 
| Kevin | Yuning | Nicholas | Nyein Su | Zachery
Hours | 89.5 | 74 | 81.5 | 77.5 | 86.5
3
Non-Programming Tasks
Chart: 
| Non Programming | Programming
Hours | 408 | 343.71
Column1
Non-Programming
54%
Programming
46%
Tasks Distribution
Notes: Explain the deviation, and more importantly why our schedule doesn’t have a regular chunk like 2 weeks.

## Slide 8
Chart: 
| Kevin | Yuning | Nicholas | Nyein Su | Zachery
Hours | 65.77 | 72.77 | 64.57 | 75.98 | 68.58
Chart: 
| Programming | Non Programming
Sales | 343.71 | 408
Column1
Programming Tasks
Programming
46%
Non-Programming
54%
3
Tasks Distribution
Notes: Explain the deviation, and more importantly why our schedule doesn’t have a regular chunk like 2 weeks.

## Slide 9
Function / Programmer | Bootstrap | CRUD Functions | Round 1 Logic | Round 2 Logic | UI | JSON Web Services
Kevin Onggo | X | X | X | X |  | X
Kong Yu Ning | X | X |  |  | X | 
Nicholas Lee |  | X | X | X | X | X
Nyein Su Aye | X | X |  |  | X | 
Zachery Pang | X |  | X | X |  | X
4
Task Allocation
Notes: Good Exposure for everyone.

## Slide 10
Chart: 
| Kevin | Yuning | Nicholas | Nyein Su | Zachery
Column2
Actual | 65.77 | 72.77 | 64.57 | 75.98 | 68.58
Column1 | 0
5
65.77
72.77
64.57
75.98
68.58
Programming Hours
Notes: Explain the deviation, and more importantly why our schedule doesn’t have a regular chunk like 2 weeks.

## Slide 11
6
Problems Faced | 
Problem / Issue | Solution / Action Taken
Tasks were too specific (too many dependencies) | Tasks were made more general
No code ownership (require time to understand code when coding) | Each member was assigned the responsibility for a specific functionality/class/UI
Ever-changing project requirements / reduces schedule estimation accuracy | PM to constantly track changes in wiki (and check with supervisor.) Utilized our buffered time to cater to the changes
Problems Faced
Notes: Explain the deviation, and more importantly why our schedule doesn’t have a regular chunk like 2 weeks.

## Slide 12
Scope of Presentation
Schedule
Metrics
Use of Subversion
Others

## Slide 13: METrics
1
2
3
4
Schedule Metrics
Pair Programming Metrics
Bug Metrics
Metrics Woes

## Slide 14
1
Schedule Metrics
Chart: Schedule Metric Score
| Iter #1 | Iter #2 | Iter #3 | Iter #4 | Iter #5 | Iter #6
Index | 100 | 100 | 100 | 95 | 100 | 100 | 0

## Slide 15
Problem / Issues | Solution / Action Taken
Feature Boxing | In our first iteration of coding there was a task which threatened to spillover as a result we decided to shift it to the next iteration
1
Schedule Metrics

## Slide 16
Chart: 
PP Index | 213 | 394 | 60 | 284 | 131 | 121 | 131 | 122 | 628 | 129 | 129 | 99 | 99 | 101 | 98 | 106 | 101 | 119 | 117 | 99 | 94 | 117 | 100 | 102 | 127 | 100 | 103 | 90 | 122 | 205 | 98 | 84 | 80 | 82 | 133 | 119 | 108 | 158 | 113
2
Acceptable
Region
Pair Programming Metrics
Iter #2
Iter #4
Iter #6

## Slide 17
Problem / Issues | Solution / Action Taken
Overestimation | Using the metrics we immediately understood that we were planning PP with too much buffers at the start, and hence sought to adjust our planning
2
Pair Programming Metrics

## Slide 18
Chart: 
| Iter #1 | Iter #2 | Iter #3 | Iter #4 | Iter #5 | Iter #6
Bug Metric Score | 23 | 1 | 3 | 4 | 6
3
Bug Metrics

## Slide 19
Problem / Issues | Solution / Action Taken
No Significant Issues | None
3
Bug Metrics

## Slide 20
4
Problem / Issues | Solution / Action Taken
No Significant Issues | None
Metrics Woes

## Slide 21
Scope of Presentation
Schedule
Metrics
Use of Subversion
Others

## Slide 22: Subversion
1
2
SVN Commits
SVN Audits

## Slide 23
Chart: 
| Iteration 1 | Iteration 2 | Iteration 3 | Iteration 4 | Iteration 5 | Iteration 6
Kevin | 0 | 13 | 6 | 5 | 3 | 10
Yuning | 0 | 4 | 6 | 23 | 15
Nyein Su | 7 | 15 | 5 | 12 | 9 | 8
Nicholas | 0 | 1 | 5 | 0 | 7 | 4
Zachery | 0 | 3 | 9 | 24 | 25 | 4
1
SVN Commits

## Slide 24
Chart: SVN Commits For Entire Project
| Kevin | Yuning | Nicholas | Nyein Su | Zachery
Commits | 37 | 51 | 17 | 61 | 73
1
SVN Commits

## Slide 25
Chart: 
| Iteration 1 | Iteration 2 | Iteration 3 | Iteration 4 | Iteration 5 | Iteration 6
Match | 0 | 22 | 14 | 37 | 17 | 11
Late | 0 | 0 | 0 | 0 | 0 | 0
No Match | 0 | 0 | 0 | 1 | 0 | 0
Unlogged | 0 | 1 | 0 | 0 | 0 | 0
Early | 0 | 1 | 1 | 3 | 0 | 0
2
2
SVN Audits

## Slide 26
Iteration | Comments
2 | PP Log #3 – Unlogged due to inexperience with Pplog and as a result set the wrong timing for PP session PP Log #7 – Early due quality assurance after committing codes
3 | PP Log #39 – Early due quality assurance after committing codes
4 | PP Log #53, #78, #82 – Early due quality assurance after committing codes PP Log #61 – Inability to Debug
2
2
SVN Audits

## Slide 27
Chart: SVN Audits For Entire Project
| Match | No Match | Late | Early | Unlogged
Sales | 108 | 1 | 0 | 4 | 1
94%
2
2
SVN Audits

## Slide 28
Scope of Presentation
Schedule
Metrics
Use of Subversion
Others

## Slide 29: OTHERs
1
2
Takeaways
Conflict Resolution
3
Interesting Facts

## Slide 30
Technical Skills
  Web Application & associated technologies
  Greater depth in Java
  New Languages: Html / CSS / Javascript
Soft Skills
  Project Management
  Teamwork
  Communications
Attitude
  “Learning to Learn”
  “Quality, quality and more quality”
  “A good progress leads to a good outcome”
Takeaways
1

## Slide 31
No actual conflicts 
At times of disagreement
  Solve it through reasoning & voting
2
Conflict Resolution

## Slide 32
Interesting Facts About Our Team Members !!!
Team Members:
Kevin Onggo
Kong Yu Ning
Nicholas Lee Cheun Qing
Nyein Su Aye
Zachery Pang Zi Qi

## Slide 33: Kevin Onggo
Likes to say that he is lazy!

## Slide 34: Kong Yu Ning
Always complain while doing or not doing work!

## Slide 35: Nicholas Lee
Is tremendously proud of his “sexy” legs

## Slide 36: Nyein Su Aye
Using a SUPER SLOWWW Mac

## Slide 37: Zachery Pang
Eats one whole roast chicken for meals

## Slide 38
The End