## Slide 1: G1 T3
PM REVIEW
YUNING
KEVIN
NYEIN SU
NICHOLAS
ZACHERY

## Slide 2: Scope of Presentation
FUNCTIONALITIES
SCHEDULE
METRICS
R & R
ROTATION PLAN FOR PP

## Slide 3
Rotation Plan for PP
Functionalities
Metrics
R & R
Schedule
ADDITIONAL
DROPPING

## Slide 4
Rotation Plan for PP
Functionalities
Metrics
R & R
Schedule
Framework

## Slide 5: Target Completion
Week 13
Rotation Plan for PP
Functionalities
Metrics
R & R
Schedule

## Slide 6
Rotation Plan for PP
Functionalities
Metrics
R & R
Schedule
Started at the end of each supervisor meeting
Supervisor Meetings
Wk2
Wk4
Wk6
Wk8
Wk10
Wk13+
Iteration 1
Iteration 2
Iteration 3
Iteration 4
Iteration 5
Iteration 6
Wk13
Notes: Supervisor meetings: Adjust the arrows

## Slide 7: Structure of Each Iteration
Rotation Plan for PP
Functionalities
Metrics
R & R
Schedule
Analysis & Design
Implementation
Integration
Testing & Debugging
Consolidate Feedbacks

## Slide 8: Structure of Each Iteration
Rotation Plan for PP
Functionalities
Metrics
R & R
Schedule
Analysis & Design
  Revise Sequence Diagram
  Revise Test Cases
  Schedule & Schedule Metrics
  PPLog
  Project Requirements / Enchancements
Implementation
  Functions
  Basic UI
Integration

## Slide 9: Structure of Each Iteration (Continued)
Rotation Plan for PP
Functionalities
Metrics
R & R
Schedule
Testing & Debugging
  Application Testing
  Application Debugging
  Quality Assurance
  Update bug metrics
Consolidate Feedbacks
  Translate the feedbacks in workable enhancements
  Factor the enhancements in schedule
  Implement enhancements in next iteration

## Slide 10: Iteration #1
Rotation Plan for PP
Functionalities
Metrics
R & R
Schedule
Wk-3 | Wk-4 | Wk-5
#1
Project Management
Application Design(Use Cases, Diagrams, Wireframe)

## Slide 11: Iteration #2
Rotation Plan for PP
Functionalities
Metrics
R & R
Schedule
Wk-5 | Wk-6 | Wk-7
#2
Bootstrapping without JSON Validation
CRUD Functionalities
Supervisor
Meeting
PM Review

## Slide 12: Iteration #3
Rotation Plan for PP
Functionalities
Metrics
R & R
Schedule
Wk-8 |  | Wk-9
#3
Functionalities (Admin)
Basic User Interface
JSON Web Service
Supervisor
Meeting
Recess Week

## Slide 13: Iteration #4
Rotation Plan for PP
Functionalities
Metrics
R & R
Schedule
Wk-9 |  | Wk-11
#4
Round and bidding Logic (2 Parts)
User Interface
Post Heuristics Improvement
Integration
Heuristics
Wk-10

## Slide 14: Iteration #5
Rotation Plan for PP
Functionalities
Metrics
R & R
Schedule
#5
Internal UAT
Enhancement of UI
Wk-11 | Wk-12 | Wk-13
UAT
Supervisor Meeting

## Slide 15: Iteration #6
Rotation Plan for PP
Functionalities
Metrics
R & R
Schedule
Wk-13 |  | Wk-13+
Final Presentation
#6
Prep for Final Presentation

## Slide 16
Rotation Plan for PP
Functionalities
Metrics
R & R
Schedule
Task | Pang Zi Qi | Kong Yu Ning | Kevin Onggo | Nyein Su Aye | Nicholas
Schedule Planning | ü | ü |  |  | 
Test Cases/Test Plans |  |  | ü |  | 
Bug Metrics |  |  | ü |  | 
Risk Assessment Plan |  | ü |  |  | 
Use case Diagrams(Draft) |  |  | ü |  | 
Logical Diagram | ü |  |  | ü | 
Sequence Diagram | ü | ü |  |  | ü
User Interface (wireframe) |  |  |  | ü | 
Diagram Compilation + Update to SVN |  |  |  | ü | 
Quality Assurance | ü |  |  | ü | 
End of Iteration meeting + Application Design walkthrough | ü | ü | ü | ü | ü
Iteration 1

## Slide 17
Rotation Plan for PP
Functionalities
Metrics
R & R
Schedule
Task | Pang Zi Qi | Kong Yu Ning | Kevin Onggo | Nyein Su Aye | Nicholas
BootStrapping (Upload, Read, Validate, Insert) | ü | ü | ü | ü | ü
Bid for Session |  |  | ü | ü | 
Drop Bid |  |  | ü | ü | 
Drop Session |  |  | ü |  | ü
Update Bid |  |  | ü |  | ü
Login |  |  |  | ü | 
Search Course |  |  | ü |  | ü
View All Bids |  | ü |  | ü | 
Deployment & Testing | ü | ü | ü | ü | ü
Iteration 2

## Slide 18: Iteration: Overall Timeline
Rotation Plan for PP
Functionalities
Metrics
R & R
Schedule
Iteration | Deliverables
#1 | Application Design(Use Cases, Diagrams, Wireframe)
#2 | Bootstrapping without JSON Validation CRUD Functionalities
#3 | Functionalities (Admin), User Interface, JSON
#4 | Round & Bidding Logic, Enhance User Interface, Integration
#5 | Internal UAT
Wk2
Wk4
Wk6
Wk8
Wk10
Wk13+
Iteration 1
Iteration 2
Iteration 3
Iteration 4
Iteration 5
Iteration 6
Wk13

## Slide 19: Iterations
Rotation Plan for PP
Functionalities
Metrics
R & R
Schedule
Iteration | Period | Buffer
#1 | 15 days | -
#2 | 14 days | -
#3 | 6 days | -
#4 | 18 days | -
#5 | 12 days | -
#6 | 6 days | -

## Slide 20: Critical Path for Iteration #1
SCHEDULE PLANNING
USE CASE
4 DAYS
2 DAYS
LOGICAL DIAGRAM/SEQUENCE DIAGRAM
3 DAYS
1 DAY
COMPILE
Rotation Plan for PP
Functionalities
Metrics
R & R
Schedule
METRICS/TEST CASE
4 DAYS
15 Days
USER INTERFACE
REVIEW USE CASE & METRICS
BUSINESS LOGIC
4 DAYS
4 DAYS
2 DAYS

## Slide 21: Critical Path for Iteration #2
BOOTSTRAPING
RESEARCH
4 DAYS
2 DAYS
FUNCTIONALITIES
6 DAYS
DEPLOYMENT
TESTING
1 DAY
1 DAY
INTEGRATION/CLEAN UP
Rotation Plan for PP
Functionalities
Metrics
R & R
Schedule
DEPLOYMENT
TESTING
&
Debugging
2 DAY
14 Days

## Slide 22: Critical Path Current Iteration #3
Rotation Plan for PP
Functionalities
Metrics
R & R
Schedule
POST SUPERVISOR MEETING
1 DAY
DEPLOY & TEST
1 DAY
4 DAYS
ADMIN FUNCTIONS
UI IMPLEMENTATION
4 DAYS
1 DAY
DEPLOY & TEST
DEBUG
1 DAY
6 Days

## Slide 23: Critical Path Iteration #4
Rotation Plan for PP
Functionalities
Metrics
R & R
Schedule
POST SUPERVISOR MEETING
2 DAYS
ROUND & BIDDING LOGIC
1 DAY
1 DAY
ROUND & BIDDING LOGIC PART 2
4 DAYS
POST
IMPROVEMENT
HEURISTICS
18 Days
HEURISTICS
PREP
1 DAY
4 DAYS
ADDITIONAL
UI REQUIREMENTS
4 DAYS
INTEGRATE
3 DAYS

## Slide 24: Critical Path Iteration #5
Rotation Plan for PP
Functionalities
Metrics
R & R
Schedule
1 DAY
DEPLOY & TEST
DEBUG
2 DAYS
INTERNAL
UAT
1 DAY
SUP MEETING PREP
2 DAYS
POST SUP IMPROVEMENT
3 DAYS
1 DAY
DEPLOY & TEST
DEBUG
3 DAYS
12 Days
1 DAY
UAT
POST UAT IMPROVEMENTS
4 DAYS
1 DAY
DEPLOY & TEST
DEBUG
1 DAY

## Slide 25: SCHEDULE METRICS
Rotation Plan for PP
Functionalities
Metrics
R & R
Schedule
Chart: 
| Iteration 1 | Iteration 2
Schedule Metrics | 100 | 100
Time-boxing
100%
100%

## Slide 26
Rotation Plan for PP
Functionalities
Metrics
R & R
Schedule
SCHEDULE
MITIGATION
PLAN
1 .Immediately, inform your supervisor
2. Re-estimate the tasks for the future iterations.
3. Use the Buffer days

## Slide 27: PAIR PROGRAMMINGMETRICS
Rotation Plan for PP
Functionalities
Metrics
R & R
Schedule
FUNCTION | PLANNED | ACTUAL | PPI | STATUS
Bootstrap |  |  |  | 
Basic MVC structure | 5 | 3.5 | 1.43 | Ok
Utility Classes | 5 | 2.35 | 2.13 | Overestimated
JSP (View / Boundary) | 5 | 0.28 | 17.65 | Overestimated
SQL Scripts | 9 | 2.28 | 3.93 | Overestimated
BootstrapDao | 9 | 14.88 | 0.60 | Ok
BootstrapDao (Clear) | 14 | 4.93 | 2.84 | Overestimated

## Slide 28: PAIR PROGRAMMINGMETRICS
Rotation Plan for PP
Functionalities
Metrics
R & R
Schedule
FUNCTION | PLANNED | ACTUAL | PPI | STATUS
Functionalities |  |  |  | 
Update Bid | 4.5 | 3.43 | 1.31 | Ok
Drop Session | 4.5 | 3.73 | 1.21 | Ok
Drop Bid | 4.5 | 3.43 | 1.31 | Ok
Bid for Session | 4.5 | 3.70 | 1.22 | Ok
View All Bids | 4.5 | 0.72 | 6.28 | Overestimated
Search Course | 4.5 | 3.50 | 1.29 | Ok
Login | 4.5 | 3.48 | 1.29 | Ok

## Slide 29: PP Mitigation
Rotation Plan for PP
Functionalities
Metrics
R & R
Schedule
Score(%) | Action
PPM < 50 | Re-estimate the tasks in the coming iteration(s) and update the schedule document. Review possible pairing & estimation issues.
50 < PPM <= 150 | No action required.
150 < PPM | Re-estimate the tasks in the coming iteration(s) ) and update the schedule document. Review possible pairing & estimation issues.

## Slide 30: PP Mitigation
Rotation Plan for PP
Functionalities
Metrics
R & R
Schedule
1 .Immediately, inform supervisor
2. Use the extra time for more research
3. Re-estimate the tasks in the coming iteration(s) ) and update the schedule document.

## Slide 31: BUG METRICS
Rotation Plan for PP
Functionalities
Metrics
R & R
Schedule
Not done testing yet.

## Slide 32: BUG Actions
Rotation Plan for PP
Functionalities
Metrics
R & R
Schedule
Internal Bug List
Our efforts at knowledge management.

## Slide 33: ROLES & RESPONSIBILITIES
Rotation Plan for PP
Functionalities
Metrics
R & R
Schedule

## Slide 34: Project Manager
Rotation Plan for PP
Functionalities
Metrics
R & R
Schedule
PM
Planning clear and feasible project objectives and schedule
Ensuring that the team adheres to the schedule
Do the necessary rectification if there are any delays in schedule
Update metrics, and ensure all documentations are updated
Set the agenda for all meeting

## Slide 35
Rotation Plan for PP
Functionalities
Metrics
R & R
Schedule
Code
Integrate
Test
Debug
1
2
3
4
DEVELOPER

## Slide 36: Rotation Plan
Rotation Plan for PP
Functionalities
Metrics
R & R
Schedule
Iteration | Project Manager | Pair 1 | Pair 2
#1 | Zachery | Yu Ning Nyein Su | Kevin Nicholas
#2 | Zachery | Zachery Nicholas | Kevin Nyein Su
#3 | Yu Ning | Yu Ning Kevin | Zachery Nyein Su
#4 | Nicholas | Yu Ning Nyein Su | Zachery Kevin
#5 | Nyein Su | Yu Ning Nicholas | Zachery Kevin
#6 | Kevin | Yu Ning Nicholas | Zachery Nyein Su

## Slide 37: Milestones for PM
Rotation Plan for PP
Functionalities
Metrics
R & R
Schedule
Iteration | Project Manager | Milestones
#1 | Zachery | -
#2 | Zachery | Supervisor Meeting
#3 | Yu Ning | PM Review
#4 | Nicholas | Heuristics
#5 | Nyein Su | UAT
#6 | Kevin | Final Presentation

## Slide 38: G1 T3
Thank you 
YUNING
KEVIN
NYEIN SU
NICHOLAS
ZACHERY