## Slide 1: SOFTWARE ENGINEERING
SUPERVISOR MEETING
G1-T3
brought to you by Blab-bers
Bid Like A Boss..

## Slide 2: Agenda
Project Management
  Goals
  Schedule
  Test plan
  Risk Assessment & Mitigation
  Members skills Development Plans
Product
  Wireframe / Added Functionality / Application Design / Prototype
Progress & Way ahead
  Planned Vs Actual
  Work Allocation
  Programming Hours
  Metrics
  Problems Faced
  Learning Points / Best Practices
  Milestones for next 2 weeks

## Slide 3
Team Goals

## Slide 4: Goals
Maintain low stress levels
To be well-prepared and ensure smooth completion of each iteration
Maintain Professionalism
Be committed to deadlines for each task to prevent snowball
Create a project which we will be proud of
A+ for SE and Credit Suisse

## Slide 5: Iterations & Milestones
Wk-3 | Wk-5 | Wk-7 | Wk-9 | Wk-11 | Wk-14
Iteration 1
Iteration 2
Iteration 3
Iteration 4
Iteration 5
Iteration | MileStones
#1 | Application Design(Use Cases, Diagrams, Wireframe)
#2 | Bootstrapping without JSON Validation CRUD Functionalities
#3 | Functionalities (Admin), User Interface, JSON
#4 | Round & Bidding Logic, Enhance User Interface, Integration
#5 | Internal UAT

## Slide 6: Iteration #1
Wk-3 | Wk-4 | Wk-5
#1
Project Management
Application Design(Use Cases, Diagrams, Wireframe)

## Slide 7: Iteration #2
Wk-5 | Wk-6 | Wk-7
#2
Bootstrapping without JSON Validation
CRUD Functionalities
Supervisor
Meeting

## Slide 8: Iteration #3
Wk-7 | Wk-8 | Wk-9
#3
Functionalities (Admin)
User Interface
JSON Web Service
Supervisor
Meeting
PM Review

## Slide 9: Iteration #4
Wk-9 | Wk-10 | Wk-11
#4
Round & Bidding Logic
Enhance User Interface
Integration
Heuristic Evaluation

## Slide 10: Iteration #5
Wk-11 | Wk-12 | Wk1-3 | 
#5
Internal UAT
Supervisor Meeting
UAT Test

## Slide 11: Iteration #6
 |  | Wk1-3 | Wk-14
Final Presentation
UAT Test

## Slide 12: Risk Assessment
S/N | Risk Statement | Risk Mitigation
1 | Team is unfamiliar with Netbeans Openshift, Bootstrap, SVN | Members who are familiar with the system will coach those who are unfamiliar All must be familiar by week 3.
2 | Team is unfamiliar with JSON, javascript, Jquery | 1. All are to research on required technologies. 2. Sharing by subject matter expert. 3. Hands-on practice on the technology. 4. Do forward planning with regard to UI to ensure that it will match up with the server side code.
3 | Mismatch between project outcome and requirements | 1. Plan first and lay out clearly the requirements. 2. Create a clear schedule metrics that adheres to the project requirements. 3. Project manager constantly ensure adherence to the requirements stipulated in the schedule metrics.
All deadlines must be strictly adhered to!!!

## Slide 13
Product

## Slide 14: Test Plan
Unit Test
Automated Test
Regression Test
Internal UAT
UAT

## Slide 15: Skills Development Plan
Pair Programming
Code ownership and remedy
Mutual Feedback
Internal Coaching & Tests

## Slide 16
Product

## Slide 17
Progress & Way Ahead

## Slide 18: Progress – Project Schedule
Start!
Bootstrapping
Functionalities
Finish Application Design
01/09
13/09
Start!
Bootstrapping
Functionalities
Finish Application Design
01/09
13/09
18/09
23/09
27/09
27/09
Planned Timeline
Actual Timeline
Deviation: JSON Reponse + Deployment & Testing (12 hours)
Notes: We were faced with some technical difficulties, and as a result am behind schedule by 2 days. To circumvent this, we are shifting the schedule back, and we will put in slightly more hours in the next iteration. You can refer to the schedule we handed to you.

## Slide 19: Work Allocation: Iteration 1
Task | Pang Zi Qi | Kong Yu Ning | Kevin Onggo | Nyein Su Aye | Nicholas
Schedule Planning | ü | ü |  |  | 
Test Cases/Test Plans |  |  | ü |  | 
Bug Metrics |  |  | ü |  | 
Risk Assessment Plan |  | ü |  |  | 
Use case Diagrams(Draft) |  |  | ü |  | 
Logical Diagram | ü |  |  | ü | 
Sequence Diagram | ü | ü |  |  | ü
User Interface (wireframe) |  |  |  | ü | 
Diagram Compilation + Update to SVN |  |  |  | ü | 
Quality Assurance | ü |  |  | ü | 
End of Iteration meeting + Application Design walkthrough | ü | ü | ü | ü | ü

## Slide 20: Work Allocation: Iteration 2
Task | Pang Zi Qi | Kong Yu Ning | Kevin Onggo | Nyein Su Aye | Nicholas
BootStrapping (Upload, Read, Validate, Insert) | ü | ü | ü | ü | ü
Bid for Session |  |  | ü | ü | 
Drop Bid |  |  | ü | ü | 
Drop Session |  |  | ü |  | ü
Update Bid |  |  | ü |  | ü
Login |  |  |  | ü | 
Search Course |  |  | ü |  | ü
View All Bids |  | ü |  | ü | 
Deployment & Testing | ü | ü | ü | ü | ü

## Slide 21
Programming Hours (Iteration #2)
Chart: 
| Zachery | Yu Ning | Kevin | Nicholas | Nyein Su | Total
Programming Hours | 3.5 | 25.5 | 27.57 | 16.47 | 27.43 | 100.47
Iteration 3 | 1
Due: Presentations & SMUX elections
Due: Project Manager
***Hours will be balanced in iteration 3.

## Slide 22: Stipulated Programming Hours (Iteration #3)
Chart: Addressing the hours disparity
| Zachery | Yu Ning | Kevin | Nicholas | Nyein Su
Iteration 2 | 3.5 | 25.5 | 27.57 | 16.47 | 27.43
Iteration 3 | 40 | 20 | 25 | 35 | 25
Column1
25hrs
35hrs
25hrs
20hrs
40hrs

## Slide 23: Metrics
 | Schedule | Bug | Pair Programming
Score | 1.0 | - | -
Action | - | - | -
Iteration 1
 | Schedule | Bug | Pair Programming
Score | 1.0 | 12 | 3.27
Action | None | Fixed Upon discovery | Slightly altered Schedule
Iteration 2

## Slide 24: Problems Faced
Overestimated /Underestimation of task complexity / duration
Schedule was too functionality oriented. Split into too many tasks.
Conflicts in subversion commits
Bottlenecks arose due to code dependency
Uneven job distribution. (Did not prepare PPLog before hand)

## Slide 25: Best Practices – Learning Points
Code first, refactor later
Be disciplined in coding and naming conventions
Knowledge management system (Code Issues Tracker)
Refurbish Schedule (See new schedule)

## Slide 26: Milestones for next 2 Weeks
Supervisor Meeting
Functionalities for Admin + UI
01/10
11/10
09/10
PM Review
Week-7
Week-8

## Slide 27: Important dates to note
Personnel | Conflicts | Date
Kong Yu Ning | Final presentation (Due: TSM Beijing) | Nov 16th – 23rd
Nicholas Lee | Credit Suisse (Due: OCSP) | Dec 8th – 25th

## Slide 28: The End