## Slide 1: G1 T3
brought to you by Blab-bers
Bid Like A Boss..

## Slide 2: Agenda
Follow-ups
Planned Vs Actual
Task Allocation
Metrics
The Way Ahead

## Slide 3: Follow-ups (Supervisor Meeting II)
Advices from Supervisor | Follow-up Actions Taken
Assign each programming task to a certain pair. | Done as requested

## Slide 4: Schedule Progress (Iter #4 - 20days)
Iter #4 Start!
UI (Pre-Heuristic)
Admin Functions & JSON
Round 1 Clearing Logic
UI Improvement
Round 2
Clearing Logic
Iteration Ends
15/10
11/10
17/10
29/10
Planned Timeline
Actual Timeline
Iter #4 Start!
UI (Pre-Heuristic)
Admin Functions & JSON
Round 1 Clearing Logic
Round-2
Clearing Logic
UI Improvements
Iteration Ends
15/10
12/10
18/10
31/10
Heuristic
Evaluation
Heuristic
Evaluation
19/10
19/10
22/10
22/10
27/10
30/10

## Slide 5: Task Allocation #4
Task | Pang Zi Qi | Kong Yu Ning | Kevin Onggo | Nicholas | Nyein Su Aye
Round -1 Clearing Logic | ü |  | ü | ü | 
UI Improvements |  | ü |  |  | ü
Admin Functions & JSON Responses (Iter #3) | ü |  | ü | ü | 
Round – 2 Clearing Logic | ü |  | ü | ü | 
Deployment & Testing | ü |  | ü |  | 
Debugging | ü | ü | ü | ü | ü
Quality Assurance | ü | ü | ü | ü | ü

## Slide 6: Programming Hours
Chart: 
| Zachery | Yu Ning | Kevin | Nicholas | Nyein Su
Iter #2 & Iter #3 | 18.5 | 35 | 38.07 | 33.75 | 36.67
Iter #4 | 32.87 | 27.83 | 12.83 | 18.22 | 29.53

## Slide 7: Current Metrics #4
 | Schedule | Bug | Pair Programming
Score | 0.95 | 3 | 1.14
Action | - | Fixed during the debugging session. | -

## Slide 9
expected

## Slide 10: Pair Programming Metric
PPM Score
0.0
0.5
1.5
Debugging
Planned Hours : 6.0
Actual Hours : 2.93

## Slide 11: Goals for Next 2 Weeks
31/10
1/11
UAT
05/11
Supervisor Meeting
09/11
10/11
Post UAT Changes
Iteration Ends!!!
(31 Oct – 14 Nov)
Preparation for
Final Presentation
Internal UAT
Iteration #4

## Slide 12: Thank You!
brought to you by Blab-bers
Bid Like A Boss..