## Slide 1: G1 T3
SUPERVISOR MEETING II
brought to you by Blab-bers
Bid Like A Boss..

## Slide 2: Agenda
Follow-ups
Current progress
Planned vs Actual
Task Allocation
Metrics
The Way Ahead

## Slide 3: Follow-ups
Advices from Supervisor | Follow-up Actions Taken
Including buffer time for schedule | Done as requested
Deploy App on Openshift | Done as requested
Notes: bug metric

## Slide 4: Completed Functions (Iteration 2)
Bootstrapping
Bid for Session
Drop Session
Drop Bid
Update Bid
Login
Search Course
View All Bids

## Slide 5: Completed Functions (Iteration 3)
JSON Responses
Admin Functions
  Start Bidding Round
  Stop Bidding Round
User Interface for Student side functions
Deployment

## Slide 6: Issues
Wrong Design Concept for User Interface
  Login page and the mainpage.jsp are combined into one (Not sustainable).

## Slide 7: Schedule Progress
Iter #3 Start!
Coding
Deployment
Testing & Debugging #2
07/10
05/10
10/10
11/10
Planned Timeline
Actual Timeline
Supervisor meeting
Iter #3 Start!
Coding
Deployment
Testing & Debugging #2
07/10
05/10
10/10
11/10
Supervisor meeting

## Slide 8: Schedule Progress
Shift to next Iteration
Update Bid (JSON)
Delete Bid (JSON)
Dump(bid, section)
Delete Bid
Drop Section
Require Validations
Changes in Validation functions
Require Round 1 Clearing Logic(Iter #4)

## Slide 9: Task Alloction #3
Task | Pang Zi Qi | Kong Yu Ning | Kevin Onggo | Nyein Su Aye | Nicholas
JSON Responses(Bootstraping, Dump tables) | ü |  |  |  | ü
Start/Stop Bidding Rounds | ü |  |  | ü | 
UI (Login, Home, Bid Status) |  | ü | ü | ü | 
UI(Populate User Details, Deliver Course Search Results) | ü |  | ü | ü | ü
UI(Populate Timetable) |  | ü |  |  | ü
UI(Add/Edit/Drop Bids) |  |  | ü |  | ü
Deployment & Testing | ü | ü | ü | ü | ü
Debugging | ü | ü | ü | ü | ü
Quality Assurance | ü | ü | ü |  | 

## Slide 10: Programming Hours #2 & #3
Chart: 
| Zachery | Yu Ning | Kevin | Nicholas | Nyein Su
Iter #2 | 3.5 | 25.5 | 27.57 | 16.47 | 27.43
Iter #3 | 15 | 9.5 | 10.5 | 17.25 | 8.75

## Slide 11: Current Metrics #3
 | Schedule | Bug | Pair Programming
Score | 1.0 | 24 | 1.045
Action | - | Stopped the development and fixed the bug immediately. | -

## Slide 12: SVN

## Slide 13: Goals for Next 2 Weeks
2 Weeks (11/10 – 29/10)
11/10
Iter #4 Start!
14/10
Heuristics
19/10
Round 1 Logic
22/10
Round 2 Logic & Post Improvements
UI Enhancement
23/10

## Slide 14: G1 T3
Thank you! 
YUNING
KEVIN
NYEIN SU
NICHOLAS
ZACHERY